## Sheet1
Task | *ETAs |  | Notes
Define Pages Types: Baby Tea, My Pregnancy, My Baby and Buy Here in IS | 2 days |  | Completed
Make relation with user email on the sign in with IS user profile | 2 days
Make sure we are tracking each category page into IS | 2 days
Define Category Attributes for each Category | 4 days
Popups for Known/Unknown Users | 10 days
| Known User | Unknown User
Popup by Page Type (Baby Shower, My Pregnancy, My Baby and Products) **Home is not included per our latest conversation. | 9hrs | 9hrs
- Style by template based on custom Design *(1) | 4hrs | 4hrs | *(1) Could be reduced after we received final creatives.
- Image and Labels formats | 1hr | 1hr
- Form (Input Fields) | 1hr | 1hr
- Form Validation (Email format, Date format, required fields) | 2hrs | 2hrs
- Date Picker | 1hr | 1hr
Landing Page or workaround related with this *(2) |  |  | *(2) This is not required anymore per our latest conversation.
Product Catalog *(3) | 2 days + 1hr |  | *(3) ETA provided, Sandro needs to confirm if we need to implement it.
- Dimmension (Category) and Attributes (Size) | 1hr
- Product Setup (107 Products) *(4) | 16hrs |  | *(4) If received the products list within the url and name, this could be reduced.
Data Extraction from SFMC *(5) | 7hrs |  | *(5) Considering we have access to the SFMC and Automation Studio, the date of birth field is in place and accesible for us, FTP activated from SFMC to IS.
Google Analytics Id capture *(6) |  |  | *(6) Pending research to provide an accurate ETA.
Total | 13 days
*Business Days